## Template
[5 empty] | Typical Project Risk Register | [14 empty] | Project:
Document no.:
[20 empty] | Rev. | Date | Prepared | Checked | Approved
1
As of…………
Identify Risks |  |  |  |  | Assess Risks |  |  | Treat Risks/ Risk Response | Control risks | [9 empty] | Stakeholder | Time Frame |  |  | Status | Comment
Risk ID | Risk Description |  |  |  | Possible Effect Cost/ Time/ Quality/ HSE (C/T/Q/H) | Probability Insignificant/Minor/Moderate/Major/Severe (1/2/3/4/5) | Serverity Of Impact Rarely/Unlikely/Occasional/Likely/Most Likely (1/2/3/4/5) | Mitigation Strategy A/T/M/AC | Action to Control & Mitigate | [5 empty] | Probability Insignificant/Minor/Moderate/Major/Severe (1/2/3/4/5) | Serverity Of Impact Rarely/Unlikely/Occasional/Likely/Most Likely (1/2/3/4/5) | Cost to Mitigate | Probability of Success | Owner | Raised Date | Deadline Date | Finished Date | Status | Comment
T1
No. | Risk Description |  |  |  | C/T/Q/H | Probability | Serverity Of Impact | Mitigation Strategy | Action to Mitigate | [5 empty] | Probability | Serverity Of Impact | CTM | POS | Owner |  |  |  | Status | Status
1 | Process design
2
2 | Civil & Structure design
3 | Piping design
4 | Mechanical design
5 | Electrical design
6 | Instrument design
7 | Procurement
8 | Construction
9 | Safety,Security Healthand Environmental
10 | Other
Legend:
| Probability - The likelihood that a risk will occur, |  |  |  | Risk Ranking Matrix | [8 empty] | The evaluation of the severity and probability
|  | Probability Description | Score | Probability of occurrence | 5 | Severe | Low | Significant | Critical | Extreme | Extreme |  | Probability of occurrence | 5 | Very high
|  | Almost certain to occur | 5 |  | 4 | Major | Low | Significant | Critical | Critical | Extreme |  |  | 4 | High |  |  |  | Must mitigate
|  | Probably will occur | 4 |  | 3 | Moderate | Low | Low | Significant | Critical | Critical | => |  | 3 | Medium |  |  | Should mitigate
|  | 50/50 chance | 3 |  | 2 | Minor | Very Low | Low | Low | Significant | Significant |  |  | 2 | Low | Consider accepting
|  | Probably not | 2 |  | 1 | Insignificant | Very Low | Very Low | Low | Low | Low |  |  | 1 | Very Low
|  | Very Unlikely | 1 |  | Level |  | Rarely | Unlikely | Occasional | Likely | Most Likely |  |  | Level |  | Very Low | Low | Medium | High | Very high | Very high
[7 empty] | 1 | 2 | 3 | 4 | 5 |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 5
[7 empty] | Serverity Of Impact | [8 empty] | Serverity Of Impact
Serverity Of Impact - The effect that risk will have on the project if it occurs,
|  | Impact or severity | Score |  |  | SAFETY |  |  | EQ COST (Baht)
|  | Very severe, few alternatives or work arounds | 5 |  | >>==>>> | Fatality |  |  |  | >50M
|  | Pretty severe, complex alternatives/ work arounds | 4 |  | >>==>>> | LTI |  |  |  | <50M
|  | Many reasonable alternatives | 3 |  | >>==>>> | Multiple Medical Treatments |  |  |  | <5M
|  | Alternatives within plan, cost | 2 |  | >>==>>> | First Aid |  |  |  | <500K
|  | Limited, no alternatives needed | 1 |  | >>==>>> | Minor incidents without injury |  |  |  | <100K
Strategy- The strategy to minimise the risk.
| Strategy Description | [6 empty] | Abbreviation
| Avoid: Risk avoidance is to eliminate the risk or protect the project objectives from its impact | [6 empty] | A
| Transfer: Risk transfer is seeking to shift the risk to a third party | [6 empty] | T
| Mitigate: Mitigation is reducing the probability and/or severity of an adverse risk event to and acceptable level | [6 empty] | M
| Accept: When the impact of a potential risk event is relatively small, the project team may decide to simply accept the risk | [6 empty] | AC
Cost to Mitigate (CTM) - The Cost to mitigate the risk.
| High |  | H
| Medium |  | M
| Low |  | L
Probability of Success (POS) - The Probability of Success
| High |  | H
| Medium |  | M
| Low |  | L
Note on H7: "5 Severe" "4 Major" "3 Moderate" "2 Minor" "1 Insignificant"
Note on I7: 5 Most Likely 4 Likely 3 Occasional 2 Unlikely 1 Rarely
Note on Q7: "5 Severe" "4 Major" "3 Moderate" "2 Minor" "1 Insignificant"
Note on R7: 5 Most Likely 4 Likely 3 Occasional 2 Unlikely 1 Rarely

## ตัวอย่าง Project Risk
[5 empty] | Risk Analysis and Management | [12 empty] | Project: | LLDPE2’s Logistics Phase (LLP) Project
[18 empty] | Document no.: |  | PTTPL-LLP-601
[18 empty] | Rev. | Date | Prepared | Checked | Approved
[18 empty] | 1 | 2016-12-16 | KN | SC | HP
[18 empty] | 2 | 2017-03-21 | KN | SC | HP
[18 empty] | 3 | 2017-08-30 | KN | SC | HP
Identify Risks |  |  |  |  | Assess Risks |  |  | Treat Risks/ Risk Response | Control risks | [7 empty] | Stakeholder | Time Frame |  |  | Status | Comment
Risk ID | Risk Description |  |  |  | Possible Effect Cost/ Time/ Quality/ HSE (C/T/Q/H) | Probability Low/ Medium/ High (1/2/3) | Serverity Of Impact Low/ Medium/ High (1/2/3) | Mitigation Strategy A/T/M/AC | Action to Control & Mitigate | [5 empty] | Cost to Mitigate | Probability of Success | Owner | Raised Date | Deadline Date | Finished Date | Status | Comment
T1
No. | Risk Description |  |  |  | C/T/Q/H | Probability | Serverity Of Impact | Mitigation Strategy | Action to Mitigate | [5 empty] | CTM | POS | Owner |  |  |  | Status | Status
1 | Process design
The OSBL PFDs and P&IDS have to incoporated all realted with equipment pacakges and issue for construction.
Process design shall not over all case.
2 | Civil & Structure design
|  | Structural detail drawings issue delay |  |  | T | 3 | 4 | M | 1. Shall commit dead line of Eng. Documents between PTTME with Subcontractors&Vendors (Zep./CIT) by written and inform to Zep./CIT Before Fab,&Erection two week (Case by Case) | [5 empty] | L | M | EM-PM | 2016-12-16 | 2017-03-21 |  | Close
|  | Structural detail drawings error |  |  | C/T/Q | 2 | 5 | M | 1. Shall commit dead line of Eng. Documents between PTTME with Subcontractors&Vendors (Zep./CIT) by written and inform to Zep./CIT Before Fab,&Erection two week (Case by Case) | [5 empty] | L | M | EM-PM | 2016-12-16 | 2017-03-21 |  | Close
|  | Equipment foundation detail drawings issue delay |  |  | T | 4 | 4 | M | 1. Shall commit dead line of Eng. Documents between PTTME with Subcontractors&Vendors (Zep./CIT) by written and inform to Zep./CIT Before Fab,&Erection two week (Case by Case) | [5 empty] | L | M | EM-PM | 2016-12-16 | 2017-03-21 |  | Close
|  | Equipment foundation detail drawings error |  |  | C/T/Q | 2 | 5 | M | 1. Shall commit dead line of Eng. Documents between PTTME with Subcontractors&Vendors (Zep./CIT) by written and inform to Zep./CIT Before Fab,&Erection two week (Case by Case) | [5 empty] | L | M | EM-PM | 2016-12-16 | 2017-03-21 |  | Close
|  | Material Specification on drawings issue delay |  |  | T | 3 | 3 | M | 1. Shall commit dead line of Eng. Documents between PTTME with Subcontractors&Vendors (Zep./CIT) by written and inform to Zep./CIT Before Fab,&Erection two week (Case by Case) | [5 empty] | L | M | EM-PM | 2016-12-16 | 2017-03-21 |  | Close
|  | Design factor is not conform to Engineering specification. |  |  | C/T | 3 | 5
|  | Structural Calculation missing |  |  | C/T/Q/H | 1 | 5
Design drawing is not conform to legal/regulation.
3 | Mechanical design
Information from vendor delay from plan.
OSBL equipment Cooling Tower pumps pump duty do not avaliable in the market. Problem Shutoff head to high/Poor BEP pump curve/budget concern
Comercial condition specify does not clear and will impact to budget such as. - INCO Term - Supervisor cost (lumsum/man-day rate?)
Scope of supply is not clear such as, - Equipment MECPRO supply arrived MEII site without Bracket and support Legs,
Manpower is not enough.
4 | Piping design
|  | Equipment drawing not final version |  |  | C/T | 3 | 4 | M | 1. Shall commit dead line of Eng. Documents between PTTME with Subcontractors&Vendors (Zep./CIT) by written and inform to Zep./CIT Before Fab,&Erection two week (Case by Case) | [5 empty] | L | M | EM-PM | 2016-12-16 | 2017-03-21 |  | Close
|  | P&IDs are not final version (IFC) |  |  | C/T | 3 | 4 | M | 1. Shall commit dead line of Eng. Documents between PTTME with Subcontractors&Vendors (Zep./CIT) by written and inform to Zep./CIT Before Fab,&Erection two week (Case by Case) | [5 empty] | L | M | EM-PM | 2016-12-16 | 2017-03-21 |  | Close
|  | Not yet submit the stress analysis report of ISBL piping plant from licensor to design structure (piping load). |  |  |  | 2 | 2 | M | 1. record Man hours Impact
|  | Piping, Fittings, Valve and special Bulk material of Pre-teament and Bio-diesel shortage and not sufficient it may lead to project delay. |  |  | C/T/Q/H | 2 | 2 |  | 1. finalize MTO and shall confirm between PTTME & Zep.2.Need to focus controlling cutting plan & erection 3.Borrow from Owner (if available)
|  | Pipe support/special pipe support design is missing. |  |  | C/T/Q | 3 | 4
|  | Actual site condition is not same as Owner's drawing. |  |  | T | 2 | 2
[5 empty] | C/T/Q | 3 | 5 | [7 empty] | L | M | EM-PM | 2016-12-16 | 2017-03-21 |  | Close
5 | Electrical design
Information from relate discipline is delay from plan.
6 | Instrument design
| Instrument interface between PTTME and other contractor is not conclude |  |  |  | C/T/Q | 2 | 2
| Instrument interface between instrument and piping (Break scope for vendor package) |  |  |  | C/T/Q | 2 | 1
| Scopes of work of Vendors (CIT: Interface Signal to scada, Zep: PCS&HCS package,Pelleton :deduster) are not conclude as per customer requirements |  |  |  | C/T/Q | 3 | 4 | M | 1.already have clarified the scope of work 2. Check additional scope of work against the contract and inform to PEM,PM 3.Organize the meeting with the vendors&customer | [5 empty] | L | M | EM-PM | 2016-12-16 | 2017-03-21 |  | Close
[5 empty] | C/T/Q | 2 | 1
7 | Procurement Civil & Structure
| Risk for often work scope and plan change and rush to award and short time to Procurement to negotiate and set strategy and we need more support when we faceTechnical problem. |  |  |  | C and T | 2 | 1
8 | Procurement Mechanical
| Critical Equipment shall be identified delivery time to protect negative impact on project schedule. These equipment have to order as early stage since during basic design phase. |  |  |  | T | 2 | 1 | M | 1.Manage by Weekly meeting& Risk work shop | [5 empty] | L | M | PPM-PM | 2016-12-16 | 2017-03-21 |  | Close
Late on deliery on site of equipment will impact on steel structure, mechnical, piping, Electrical and instrument of ISBL. This can make delay on M/C on project.
| Risk for Delay Payment not on time as PO mention to Oversea vendor (JANSENS & DIEPERINK and PELLETRON CORPORATION) |  |  |  | T | 2 | 1 | M | 1.Received advanced payment bond from J&D 2. Payment on the process | [5 empty] | L | M | PPM-PM | 2016-12-16 | 2017-03-21 |  | Close
| Risk for delay purchase SILO - VENT FILTER PACKAGE |  |  |  | C and T | 2 | 1 | M | 1. Already issue P/O | [5 empty] | L | M | PPM-PM | 2016-12-16 | 2017-03-21 |  | Close
9 | Procurement Piping
| Need MR PIPING & BULK MATERIAL ontime |  |  |  | T | 2 | 1
10 | Procurement Electrical
11 | Procurement Instrument
12 | Construction (General)
Sub-contractor has low perfomance
Sub-contractor has financial problem.
- Construction permit in PTTGC area delayed.
Construction drawing is not latest revision.
Work interfering between other Sub EPC Contractors, EPCm and GGC project team in many areas maybe work obstruction.
12 | Construction for Civil work
| Underground properties is not locate as shown in drawings. |  |  |  | C/T/Q/H | 3 | 4 | M | 1.Weekly expedite to PTTGC | [5 empty] | L | M | CM-PM | 2016-12-16 | 2017-03-21 |  | Close
Permit for waste removal is delay.
[5 empty] | C/T/Q | 3 | 3 | M | 1.Up dated the catch up plan | [5 empty] | L | M | CM-PM | 2016-12-16 | 2017-03-21 |  | Close
13 | Construction for Structure work
[8 empty] | M | 1.Up dated the catch up plan | [5 empty] | L | M | CM-PM | 2016-12-16 | 2017-03-21 |  | Close
14 | Construction for Mechanical work
| - Delay of on site delivery of critical equipments. |  |  |  | C/T/Q | 4 | 4 | M | 1.Up dated the catch up plan | [5 empty] | L | M | CM-PM | 2016-12-16 | 2017-03-21 |  | Close
| Unexpected requiredment from Owner such as safety requirement. |  |  |  | C/T/Q | 4 | 4 | M | 1.Prepare more detail schedule and investigate the relocation work can complete within 7 days or not, If not supply Tempo. Chiller | [5 empty] | L | M | CM-PM | 2016-12-16 | 2017-03-21 |  | Close
Equipment is not conform to specifivcation/AVL such as ( material, color etc.)
| - Heavy lifting crane availability and any damage /failure of crane during assembly ,test or during lifting. |  |  |  | C/T/Q/H | 3 | 5 | M | 1.Heavy Lifting Crane work is included in piping/mechanical subcontractor scope 2. PTTME will Expedite the subcontractor to select the crane company and specify conditions of controlling the duration periods | [5 empty] | L | M | CM-PM | 2016-12-16 | 2017-03-21 |  | Close
15 | Construction for Piping work
| Late on delivery of piping, Valves and bulk materials will impact on piping, Electrical and instrument. This can make delay on M/C on project. |  |  |  | C/T/Q | 4 | 5 | M | 1.Procument negotiate for two partial lots April &June 2017 | [5 empty] | L | M | CM-PM | 2016-12-16 | 2017-03-21 |  | Close
Piping, Fittings, Valve and special Bulk material of Pre-teament and Bio-diesel shortage and not sufficient it may lead to project delay.
16 | Construction for Electrical work
| - Shutdown and Tie-in_has short peroid and may be risked to finish on schedul. |  |  |  | (C/T/Q/H) | 3 | 3 | M | 1.Customer allows to work on Sundays only,hence PTTME will build detail plan with E&I subcontractor | [5 empty] | L | M | CM-PM | 2016-12-16 | 2017-03-21 |  | Close
power cable has defect and need to re-purchase.
Material shortage
17 | Construction for Instrument work
-
18 | Commissioning
| - | Delay in construction turnover package to commissioning(MC) and completed document package. |  |  | C/T | 4 | 4 | M | 1) Control schedule and update status on weekly meeting and/or daily meeting, shall be set-up. 2) if delay in construction work, shall be catch up plan. | [5 empty] | L | M | CM-PM | 2016-12-16 | 2017-03-21 |  | Close
| - | Delay in construction punch"A and B" clearing after final line check and PSSR close-out |  |  | C/T | 4 | 4 | M | Construction shall be plan for punch"A and B" clearing on master schedule | [5 empty] | L | M | CM-PM | 2016-12-16 | 2017-03-21 |  | Close
| - | Problem in VENDOR's equipment and/or unit package during equipment running test and/or commissioning, this cause may be correct to long time. |  |  | C/T/Q | 4 | 4 | M | 1) VENDOR's print and relate document shall be submit as plan 2) VENDOR's package close-out document befor handover to commissioning shall be completed check by QC 3) VENDOR's supervisor shall be advice/participate on them scope during commissioning and performance test run period. | [5 empty] | L | M | CM-PM | 2016-12-16 | 2017-03-21 |  | Close
Noise of flushing and Steam blow may distrub public community
Fire Fighting System test does not conform with designed code and standard may cause of schedule delay.
Hydro test water for Tank and Pipping is not enough.
Nitrogen blanket for Tank and Pipping is not available.
19 | Document/ IT
-
20 | Vendors & Suppliers
| Delay in vendor prints submission in order to get code 1 or certified/ final version before release IFC drawings to subcontractor/ construction team |  |  |  | C/T/Q | 3 | 3 | M | 1. Shall commit dead line of Eng. Documents between PTTME with Subcontractors&Vendors (Zep./CIT) by written and inform to Zep./CIT Before Fab,&Erection two week (Case by Case) | [5 empty] | L | M | CM-PM | 2016-12-16 | 2017-03-21 |  | Close
21 | Engineering Management
| Engineering design phase take longer than the baseline schedule. resulting in engineering is not complete on time - not ready for detailed design which will delay engineering and overall project schedule and extra cost for engineering team |  |  |  | C/T/Q | 4 | 4 | M | 1. Shall commit dead line of Eng. Documents between PTTME with Subcontractors&Vendors (Zep./CIT) by written and inform to Zep./CIT Before Fab,&Erection two week (Case by Case) | [5 empty] | L | M | CM-PM | 2016-12-16 | 2017-03-21
| Scope changes (positive/ negative change request) during detailed design & engineering phase before proceeding with construction work (scope change is not authorized to proceed until it is approved from OWNER) 1. Hot insulation for HCS & HCR lines 2. New substation room no.2 3. Extennded CCR 4. Approval of claim vendor listing 5. Etc. |  |  |  | C/T/Q | 5 | 5 | M | 1.Clarify Changes with Owner 2. all disciplines have to inform cost impacts invovled the changes after change approval to project control&PEM 3. Purpose cost to customer/management to approve before proceeding work of the changes 4. Manage the changes as per Project internal weekly MOM committed | [5 empty] | L | M | CM-PM | 2016-12-16 | 2017-03-21 |  | Close
| Agreement on scope of supply – interface between PTTME & other contractor are not concluded yet |  |  |  | C/T/Q | 3 | 3 | M | 1.Expedite through weelk meetin with owner | [5 empty] | L | M | CM-PM | 2016-12-16 | 2017-03-21 |  | Close
22 | Government
Control Schedule No comment
Legend:
| Probability - The likelihood that a risk will occur, |  |  |  | Risk Ranking Matrix | [8 empty] | The evaluation of the severity and probability
|  | Probability Description | Score | Probability of occurrence | 5 | Very high | Small | Moderate | Major | Major | Severe |  | Probability of occurrence | 5 | Very high
|  | Almost certain to occur | 5 |  | 4 | High | Small | Moderate | Moderate | Major | Severe |  |  | 4 | High |  |  |  | Must mitigate
|  | Probably will occur | 4 |  | 3 | Medium | Small | Small | Moderate | Major | Major | => |  | 3 | Medium |  |  | Should mitigate
|  | 50/50 chance | 3 |  | 2 | Low | Small | Small | Moderate | Moderate | Major |  |  | 2 | Low | Consider accepting
|  | Probably not | 2 |  | 1 | Very Low | Small | Small | Small | Moderate | Major |  |  | 1 | Very Low
|  | Very Unlikely | 1 |  | Level |  | Very Low | Low | Medium | High | Very high |  |  | Level |  | Very Low | Low | Medium | High | Very high | Very high
[7 empty] | 1 | 2 | 3 | 4 | 5 |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 5
[7 empty] | Serverity Of Impact | [8 empty] | Serverity Of Impact
Serverity Of Impact - The effect that risk will have on the project if it occurs,
|  | Impact or severity | Score |  |  | SAFETY |  |  | EQ COST (Baht)
|  | Very severe, few alternatives or work arounds | 5 |  | >>==>>> | Fatality |  |  |  | >50M
|  | Pretty severe, complex alternatives/ work arounds | 4 |  | >>==>>> | LTI |  |  |  | <50M
|  | Many reasonable alternatives | 3 |  | >>==>>> | Multiple Medical Treatments |  |  |  | <5M
|  | Alternatives within plan, cost | 2 |  | >>==>>> | First Aid |  |  |  | <500K
|  | Limited, no alternatives needed | 1 |  | >>==>>> | Minor incidents without injury |  |  |  | <100K
Strategy- The strategy to minimise the risk.
| Strategy Description | [6 empty] | Abbreviation
| Avoid: Risk avoidance is to eliminate the risk or protect the project objectives from its impact | [6 empty] | A
| Transfer: Risk transfer is seeking to shift the risk to a third party | [6 empty] | T
| Mitigate: Mitigation is reducing the probability and/or severity of an adverse risk event to and acceptable level | [6 empty] | M
| Accept: When the impact of a potential risk event is relatively small, the project team may decide to simply accept the risk | [6 empty] | AC
Cost to Mitigate (CTM) - The Cost to mitigate the risk.
| High |  | H
| Medium |  | M
| Low |  | L
Probability of Success (POS) - The Probability of Success
| High |  | H
| Medium |  | M
| Low |  | L
Note on F36: same as 4.1

## AT5
Risk Matrix / Map
The Risk Matrix is derived from the Risk Likelihood and Consequences/Impacts and it has been modified specifically to align with the Project’s objectives. The resulting risk matrix and associated likelihood and consequences/impacts levels are defined below: Below Table are provides suggested scales Consequence for use in Project Risk Assessments based on GCME’s Investment Risk Management Manual. Project teams are advised to review the categories and determine a scale that is relevant to their project, in particular the ‘Cost’ and 'Schedule Slippage' categories should be modified to be specific to each Project. All fields should be reviewed and amended/deleted as required prior to commencing the brainstorming session.
[9 empty] | Financial | Safety, Health & Environment |  | Supplier/Customers/ Partners |  | Law and Regulation | Reputation/Image |  | Deviation | Financial | Safety, Health & Environment |  | Supplier/Customers/ Partners |  | Law and Regulation | Reputation/Image
[9 empty] | Schedule Impact Exposure to loss from a project not meeting its schedule objectives. Cost Probability of loss due to cost overrun (Also includes decreases in revenue/EBITDA.) | Safety and Health A situation or circumstance that includes the possibility of injury to someone or of damage to property. | Environment Actual or potential threat of adverse effects on living organisms and environment by effluents, emissions, wastes, resource depletion, etc., arising out of an organization's activities. | Supplier | Customers |  | Reputation & Image The risk that a company will lose potential business because its character has been called into question. | Negative News |  | EBITDA (%, Amount) | People | Environmental | Supplier | Customers |  | Reputation and Image | Negative News | Deviation
| IMPACT (CONSEQUENCE) | 5 Severe | Low | Significant | Critical | Extreme | Extreme | 5 Severe | Project Delay : X > 20% of project timeframe or > 6 months Cost Overrun : X > 20% of total project cost EBITDA : Having > 20% impact on 1st full-year EBITDA of the project | Single or Multiple Fatalities - permanent injury or disability, many disabilities or death > 1 person. Severely affects health. The communities surrounding the factory were affected by occupation and had to evacuate the area for > 1 year. There are employees or contractors to strike, stop work. | Significant harm with widespread effect. Recovery measurable longer than 1 year to recover. Limited prospect of full recovery. | Partner : Cancellation of the contract for the sale of goods and services Affects sales > 50% of sales/year | Customer: Towards the (Boycott) purchase of goods and services Affects sales > 50% of sales/year | [Black Swan] The company was delisted from the stock exchange. Illegal criminal or civil law and order the company to stop doing business. License revoked or temporarily suspend. | [Black Swan] reputation and image of the company severe damage severely affected confidence And it is a national issue that the relevant ministries or government agencies are monitoring. Review and jointly take corrective action. Disaster with potential to lead to collapse of the project. Long term regional impact. | Received complaints as negative news There is news in foreign media. | Below target >50% | Project Delay : X > 20% of project timeframe or > 6 months Cost Overrun : X > 20% of total project cost EBITDA : Having > 20% impact on 1st full-year EBITDA of the project | บาดเจ็บสาหัส ทุพพลภาพจำนวนมาก หรือเสียชีวิต > 1 คน ส่งผลกระทบต่อสุขภาพรุนแรง ชุมชนรอบโรงงานได้รับผลกระทบในการประกอบอาชีพจนต้องอพยพออกจากพื้นที่ เป็นเวลา > 1 ปี มีพนักงานหรือผู้รับเหมานัดหยุดงานประท้วง,หยุดงาน | เสียหายเฉียบพลัน รุนแรง เป็นวงกว้าง ยากต่อการฟื้นฟู หรือใช้เวลาฟื้นฟูมากกว่า 1 ปี | คู่ค้า : ยกเลิกสัญญาธุรกรรมการขายสินค้าและบริการ ส่งผลกระทบต่อยอดขาย > 50% ของยอดขาย/ปี | ลูกค้า : ต่อด้าน (Boycott) การซื้อสินค้าและบริการ ส่งผลกระทบต่อยอดขาย > 50% ของยอดขาย/ปี | [Black Swan] บริษัทถูกถอดถอนออกจากตลาดหลักทรัพย์ ผิดกฎหมายอาญาหรือกฎหมายแพ่งและมีคำสั่งให้บริษัทหยุดดำเนินธุรกิจ ถูกเพิกถอนใบอนุญาต หรือหยุดดำเนินการชั่วคราว | [Black Swan] ชื่อเสียงและภาพลักษณ์ของบริษัทฯ เสียหายรุนแรง ส่งผลต่อความเชื่อมั่นอย่างรุนแรง และเป็นประเด็นในระดับประเทศที่กระทรวงหรือหน่วยงานภาครัฐที่เกี่ยวข้องมีการติดตาม ตรวจสอบและร่วมดำเนินการแก้ไข | ได้รับข้อร้องเรียนเป็นข่าวในด้านลบ มีข่าวออกสื่อต่างประเทศ | ต่ำกว่าเป้าหมาย >50%
|  | 4 Major | Low | Significant | Critical | Critical | Extreme | 4 Major | Project Delay: X ≥ 10% of project timeframe or > 3 months Cost Overrun: X ≥ 10% of total project cost •EBITDA : Having X ≥ 10% impact on 1st full-year EBITDA of the project | Major or Multiple Injuries - permanent injury or disability or to the point of disability or death. Affects a lot of health. There are protests or formal complaints. | Significant harm with local effect. Causes a lot of damage to the environment. It takes more than 6-12 months to recover. | Losing major partners Major partners are unable to deliver goods or services. | Lose a big customer Trading volume of major products decreased by more than 20% Major customers are unable to pay for products. | Illegal, criminal or civil law. or in violation of the Company's regulations, criminal penalties, imprisonment and fines. | Reputation and image damage was so severe that it resulted in the lack of confidence in outsiders or organizations. A critical event which requires extraordinary management effort. Localised, long term impact with unmanageable outcomes. | Received complaints as negative news. There is news in the media at the national level. | Below target >30%-50% | Project Delay: X > 10% of project timeframe or > 3 months Cost Overrun: X > 10% of total project cost •EBITDA : Having X > 10% impact on 1st full-year EBITDA of the project | บาดเจ็บสาหัส จนถึงขั้นทุพพลภาพหรือเสียชีวิต ส่งผลกระทบต่อสุขภาพมาก มีการชุมนุมประท้วงหรือมีการร้องเรียนอย่างเป็นทางการ | ทำให้สิ่งแวดล้อมเสียหายมาก ต้องใช้เวลาในการฟื้นฟูมากกว่า 6-12 เดือน | สูญเสียคู่ค้ารายใหญ่ ปริมาณการซื้อขายรายผลิตภัณฑ์หลักลดลงมากกว่า 20% คู่ค้ารายใหญ่ไม่สามารถส่งมอบสินค้าหรือบริการได้ | สูญเสียลูกค้ารายใหญ่ ปริมาณการซื้อขายรายผลิตภัณฑ์หลักลดลงมากกว่า 20% ลูกค้ารายใหญ่ไม่สามารถชำระค่าสินค้าได้ | ผิดกฎหมายอาญาหรือกฎหมายแพ่ง หรือผิดข้อบังคับของบริษัทฯ มีโทษทางอาญา จำคุกและปรับ | ชื่อเสียงและภาพลักษณ์ของบริษัทฯ เสียหายมากจนส่งผลให้บุคคลหรือองค์กรภายนอกขาดความเชื่อมั่นต่อบริษัทฯ อย่างมาก | ได้รับข้อร้องเรียนเป็นข่าวในด้านลบ มีข่าวออกสื่อในระดับประเทศ | ต่ำกว่าเป้าหมาย >30%-50%
|  | 3 Moderate | Low | Low | Significant | Critical | Critical | 3 Moderate | Project Delay: 6% ≤ X < 10% of project timeframe or < 3 months Cost Overrun: 6% ≤ X < 10% of total project cost EBITDA: Having 6% ≤ X < 10% impact on 1st full-year EBITDA of the project | Serious Injuries require Medical Treatment, or Lost Work Case. Moderate impact on health and long-term morale | Moderate harm with possible wider effect. Recovery measurable 3-6 months to recover. | Major partners Make a letter expressing dissatisfaction (Official Complain) Major partners are able to deliver some products or services. | Major customers Make a letter expressing dissatisfaction (Official Complain) Trading volume of major products decreased by 10-20% Major customers can deliver some products or services. | May make it unlawful. or the regulations of the company (Non-compliance with laws/Articles of association). | Affects the reputation and image of the Company Moderately causes dissatisfaction from the community or the public. A serious event which requires additional management effort. Localised, long term impact but manageable. | It's negative news. There is news released in the media at the provincial and regional level. | Below target >10%-30% | Project Delay: 6% < X < 10% of project timeframe or < 3 months Cost Overrun: 6% < X < 10% of total project cost EBITDA: Having 6% < X < 10% impact on 1st full-year EBITDA of the project | บาดเจ็บค่อนข้างมาก ต้องได้รับการรักษาทางการแพทย์ ไม่ถึงขั้นทุพพลภาพ แต่ต้องหยุดงาน ส่งผลกระทบต่อสุขภาพปานกลางและขวัญกำลังใจระยะยาว | ทำให้สิ่งแวดล้อมเสียหายปานกลาง ใช้เวลาในการฟื้นฟู 3-6 เดือน | คู่ค้ารายใหญ่ ทำหนังสือแสดงความไม่พอใจ (Official Complain) ปริมาณการซื้อขายรายผลิตภัณฑ์หลักลดลง 10-20% คู่ค้ารายใหญ่สามารถส่งมอบสินค้าหรือบริการได้บางส่วน | ลูกค้ารายใหญ่ ทำหนังสือแสดงความไม่พอใจ (Official Complain) ปริมาณการซื้อขายรายผลิตภัณฑ์หลักลดลง 10-20% ลูกค้าค้ารายใหญ่สามารถส่งมอบสินค้าหรือบริการได้บางส่วน | อาจทำให้ไม่เป็นไปตามกฎหมาย หรือข้อบังคับของบริษัทฯ (Non-compliance with laws/Articles of association) | กระทบต่อชื่อเสียงและภาพลักษณ์ของบริษัทฯ ปานกลาง ทำให้เกิดความไม่พอใจจากชุมชนหรือสาธารณะ | เป็นข่าวในด้านลบ มีข่าวออกสื่อระดับจังหวัดภูมิภาค | ต่ำกว่าเป้าหมาย >10%-30%
|  | 2 Minor | Very Low | Low | Low | Significant | Significant | 2 Minor | Project Delay: 3% ≤ X < 6% of project timeframe or < 2 months Cost Overrun: 3% ≤ X < 6% of total project cost as BOD approval EBITDA: Having 3% ≤ X < 6% impact on 1st full-year EBITDA of the project | Minor Injuries require Medical Treatment with/or Restricted Work Case. Low impact on health and short-term morale | Less damage to the environment. Recovery measurable less than 3 months to recover. | Verbal complains. Retail partners are unable to deliver goods or services. | Customers express dissatisfaction (Verbal complains). Trading volume of major products decreased by 5-10%. Retail customers are unable to pay for products. Retail partners are unable to deliver goods or services. | May cause non-conformance. or standards within the company (Non-conformance). | Affects the reputation and image of the company slightly, can be corrected in a short period of time. An adverse event which can be absorbed with some management effort. Localised, short term impact. | Receive complaints from the community through informal company channels It's negative news. There is news in the local media. | Below target >5-10% | Project Delay: 3% < X < 6% of project timeframe or < 2 months EBITDA: Having 3% < X < 6% impact on 1st full-year EBITDA of the project Cost Overrun: 3% < X < 6% of total project cost as BOD approval | บาดเจ็บต้องได้รับการรักษาทางการแพทย์ หรือมีคำสั่งให้ปฏิบัติงานหน้าที่อื่น ส่งผลกระทบต่อสุขภาพน้อยและขวัญกำลังใจระยะสั้นๆ | ทำให้สิ่งแวดล้อมเสียหายน้อย ใช้เวลาในการฟื้นฟูน้อยกว่า 3 เดือน | คู่ค้าแสดงความไม่พอใจ (Verbal complains) ปริมาณการซื้อขายรายผลิตภัณฑ์หลักลดลง 5-10% ลูกค้ารายย่อยไม่สามารถชำระค่าสินค้าได้ คู่ค้ารายย่อยไม่สามารถส่งมอบสินค้าหรือบริการได้ | ลูกค้าแสดงความไม่พอใจ (Verbal complains) ปริมาณการซื้อขายรายผลิตภัณฑ์หลักลดลง 5-10% ลูกค้ารายย่อยไม่สามารถชำระค่าสินค้าได้ คู่ค้ารายย่อยไม่สามารถส่งมอบสินค้าหรือบริการได้ | อาจทำให้ไม่เป็นไปตามข้อกำหนด หรือมาตรฐานภายในบริษัทฯ (Non-conformance) | กระทบต่อชื่อเสียงและภาพลักษณ์ของบริษัทฯ เล็กน้อย สามารถแก้ไขได้ในระยะเวลาสั้น | ได้รับข้อร้องเรียนจากชุมชนผ่านช่องทางบริษัทอย่างไม่เป็นทางการ เป็นข่าวในด้านลบ มีข่าวออกสื่อท้องถิ่น | ต่ำกว่าเป้าหมาย >5-10%
|  | 1 Insignificant | Very Low | Very Low | Low | Low | Low | 1 Insignificant | Project Delay: X < 3% of project timeframe or < 1 month Cost Overrun: X < 3% of total project cost EBITDA: Having X < 3% impact on 1st full-year EBITDA of the project | First Aid Case There were no injuries or minor injuries at first aid level. No effect or minimal impact on health and morale. | No impact on baseline environment. Localized to point source. No recovery required. | Retail partners Dissatisfied, complained back. Retail partners can deliver some products or services. | Retail customers Dissatisfied, complained back. Product trading volume dropped below 5% Retail customers can pay for some products. | Failure to comply with laws or regulations. but in a way that can be easily fixed. | Little impact on reputation and image of the company. Impact can be absorbed through normal activity. Localised temporary impact. | It's not a trend in the local media. | Below target <5% | Project Delay: X < 3% of project timeframe or < 1 month Cost Overrun: X < 3% of total project cost EBITDA: Having X < 3% impact on 1st full-year EBITDA of the project | ไม่มีการบาดเจ็บหรือบาดเจ็บเล็กน้อยในระดับปฐมพยาบาล ไม่มีผลหรือมีผลกระทบต่อสุขภาพและขวัญกำลังใจน้อยมาก | ไม่ส่งผลกระทบต่อสิ่งแวดล้อมหรือเสียหายน้อยมาก | คู่ค้ารายย่อย ไม่พอใจร้องเรียนกลับมา ปริมาณการซื้อขายรายผลิตภัณฑ์ลดลงต่ำกว่า 5% คู่ค้ารายย่อยส่งมอบสินค้าหรือบริการได้บางส่วน | ลูกค้ารายย่อย ไม่พอใจร้องเรียนกลับมา ปริมาณการซื้อขายรายผลิตภัณฑ์ลดลงต่ำกว่า 5% ลูกค้ารายย่อยชำระค่าสินค้าได้บางส่วน | บกพร่องในการดำเนินการตามกฎหมายหรือข้อกำหนด แต่อยู่ในวิสัยที่สามารถแก้ไขได้โดยง่าย | กระทบต่อชื่อเสียงและภาพลักษณ์ของบริษัทฯ น้อยมาก | ไม่เป็นกระแสในสื่อท้องถิ่น | ต่ำกว่าเป้าหมาย <5%
LIKELIHOOD (FREQUENCY)
|  |  | 1 | 2 | 3 | 4 | 5
|  |  | Rarely | Unlikely | Occasional | Likely | Most Likely
| Probability | Probability of Fture Events | < 5% | 5% - 10% | >10% - 25% | >25% - 50% | > 50%
|  |  | Highly unlikely to occur on this project | Given current practices and procedures, this event is unlikely to occur on this project | This event has occurred on a similar project | Event is Likely to occur on this project | Event is very likely to occur on this project, possibly several times
|  | Probability of Past Events | Never happened or may occur over a period of more than 3 years | Has happened once in the past 3 years in an industry or business or system similar to that of GCME. | Has happened more than once in the past 3 years in an industry or business or system similar to that of GCME. | Has happened 1 time locally or more times in the GCME in the past 1 year. | Has happened more than 1 time locally in the past 1 year in GCME
| Experience / Capability to control | Work process/ Ability to Control | The workflow is simple. and less chance of error There is a good audit or control. Has a very good control ability. | The workflow is more complicated. But there is also good monitoring or control. Have good control ability | The work process is complicated. But there is a check or moderately controlled. Have some or moderate control ability | The work process is complicated. and there are few checks or still have little control. Little control ability | The workflow is very complicated. and no inspection or has never been regulated. There is little or no control ability.
|  | Past Experience and Success | Have direct experience in that business or job | Very experienced in a similar business or type of work | Have some or moderate experience in that business or job | little experience in that business or job | Little or no experience in that business or job
| Probability | Probability of Fture Events | < 5% | >10% - 25% | >10% - 25% | >25% - 50% | > 50%
|  |  | Highly unlikely to occur on this project | Given current practices and procedures, this incident is unlikely to occur on this project | Incident has occurred on a similar project | Incident is likely to occur on this project | Incident is very likely to occur on this project, possibly several times
|  | Probability of Past Events | ไม่เคยเกิดขึ้น หรืออาจเกิดขึ้นได้ในระยะเวลามากกว่า 3 ปี | เคยเกิดขึ้น 1 ครั้งใน 3 ปีที่ผ่านมา ในอุตสาหกรรม หรือธุรกิจ หรือระบบ ที่ใกล้เคียงกับของ GC Group | เคยเกิดขึ้นมากกว่า 1 ครั้งใน 3 ปีที่ผ่านมา ในอุตสาหกรรม หรือธุรกิจ หรือระบบ ที่ใกล้เคียงกับของ GC Group | เคยเกิดขึ้น 1 ครั้งในพื้นที่ หรือมากกว่า 1 ครั้ง ใน GC Group ใน 1 ปี ที่ผ่านมา | เคยเกิดขึ้น มากกว่า 1 ครั้งในพื้นที่ ใน 1 ปีที่ผ่านมา ใน GC Group
| Experience / Capability to control | กระบวนการทำงาน/ ความสามารถในการควบคุม | กระบวนการทำงานง่าย และโอกาสเกิดข้อผิดพลาดน้อย มีการตรวจสอบหรือการควบคุมที่ดีรัดกุม มีความสามารถในการควบคุมดีมาก | กระบวนการทำงานซับซ้อนขึ้น แต่ยังมีการตรวจสอบหรือการควบคุมที่ดี มีความสามารถในการควบคุมที่ดี | กระบวนการทำงานซับซ้อน แต่มีการตรวจสอบ หรือควบคุมพอสมควร มีความสามารถในการควบคุมอยู่บ้างหรือระดับปานกลาง | กระบวนการทำงานซับซ้อน และมีการตรวจสอบน้อย หรือยังมีการควบคุมน้อย ความสามารถในการควบคุมน้อย | กระบวนการทำงานซับซ้อนมาก และไม่มีการตรวจสอบ หรือยังไม่เคยมีการควบคุม มีความสามารถในการควบคุมน้อยมากหรือไม่มีเลย
|  | ประสบการณ์และความสำเร็จที่ผ่านมา | มีประสบการณ์โดยตรง ในธุรกิจหรืองานนั้นๆ | มีประสบการณ์มาก ในธุรกิจหรือลักษณะงานที่ใกล้เคียงกัน | มีประสบการณ์อยู่บ้างหรือระดับปานกลาง ในธุรกิจหรืองานนั้นๆ | มีประสบการณ์น้อย ในธุรกิจหรืองานนั้นๆ | มีประสบการณ์น้อยมากหรือไม่มีเลย ในธุรกิจหรืองานนั้นๆ
|  | Key | Priority (1 is highest) | Description
|  | Extreme | 1 | Serious risk and need action & risk reduction plan immediately
|  | Critical Risk | 2 | Immediate attention / action required to mitigate the risk.
|  | Significant Risk | 3 | Action should be taken to compensate for the risk.
|  | Low Risk | 4 | Action as soon as practicable and should be taken to monitor the risk.
|  | Very Low Risk | 5 | Low priority, possibly no action required or routine acceptance of the risk.
|  | Risk Status | Description
|  | Identified | New item identified and awaiting action.
|  | Closed | Item closed e.g. no longer a concern, rejected, etc.
|  | In-progress | Item undergoing treatment/mitigation activities.
|  | Monitoring | Treatment/Mitigiation activities complete and being monitored.
|  | Implemented | Item resolved through treatment/mitigation actions and resolution accepted by stakeholders.